# Engagement Charter — Digital Lending Portfolio Optimization

## Section 1 - Objective

Strengthen credit-risk assessment, enable early delinquency detection, and optimise pricing and product strategy to grow the book on a risk-adjusted basis.

## Section 2 - Scope

- customer/loan/repayment/behavioural data analysis

- risk and value segmentation

- early-warning system design

- pricing/tenure/approval policy recommendation

- executive monitoring dashboard.

## Out of Scope

- fraud detection and KYC/AML review

- regulatory capital and IFRS 9 ECL provisioning

- collections operations design

- production build, deployment, and monitoring of the EWS

- funding strategy and asset-liability management

- full macroeconomic stress testing beyond sensitivity ranges

- channel-partner commercial renegotiation

- customer-facing product or UX changes

- organisational design and hiring

- vendor selection

- live (non-mock) dashboard tooling

## Section 3 - Success Metrics

- Reduction in 90+ DPD / credit loss rate

- Improvement in risk-adjusted return (RAROC or NIM-after-loss)

- CAC payback months and CLV by segment

- Share of losses pre-empted by EWS flags, and average lead time in days

- (Optional) Approval-rate trade-off — volume given up per loss avoided

## Section 4 - Definitions

#### DPD = Days Past Due

- Default — a loan that has ever reached 90+ DPD (an event; once flagged, stays flagged).

- Delinquency — a loan that is currently 1+ DPD (a status; can roll forward or cure).

- DPD buckets — Current / 1–30 / 31–60 / 61–90 / 90+ days past due, measured from the oldest unpaid installment.

- Vintage — loans grouped by origination month.

- Cohort observation window — 18–24 months of monthly snapshots.

## Section 5 — Final deliverable shape

Two artefacts, sharing one storyline and one set of numbers:

- Credit Policy Recommendation Report — 4–6 pages, addressed to the CRO. Recommendation on page 1. Dense, defensible, risk-adjusted.

- Stakeholder Presentation Deck — 12–14 slides, one message per slide, recommendation visible by slide 2.

The recommendation itself will take this form: one headline policy + 2–3 supporting levers. Each lever will state:

- Quantified impact — Δ default, Δ volume, Δ revenue, net Δ risk-adjusted contribution, as ranges with stated assumptions.

- Implementation owner — the named function that will execute the change.

- Guardrail metric — the indicator that would trigger pause or rollback.

The deck and report read from the same controlled workbook; every figure reconciles.